## Slide 1
Product Roadmap
HDB Maintenance & Estate Services Digital Transformation
Digital Services Office
Sample Input File — For Upload into CharterOS

## Slide 2
PRODUCT EPICS
# | Epic Name | Duration | Priority | Owner | Key Outcome
1 | Digital Intake & Triage Engine | 3 months | HIGH | Tech Lead | AI classifies and routes 75%+ of requests automatically
2 | Resident Status Visibility | 2 months | HIGH | Product Manager | Real-time SMS/push updates at every stage
3 | Officer Operations Dashboard | 3 months | MEDIUM | Product Manager | Mobile app + AI-prioritised queue for officers
4 | Contractor Digital Integration | 3 months | MEDIUM | Tech Lead | Digital work orders and SLA breach alerts
5 | Analytics & Continuous Improvement | 2 months | LOW | Product Owner | Estate-level dashboards and predictive signals

## Slide 3
DELIVERY PHASES
Phase 1 — Foundation
Months 1–3
• Digital intake form
• AI triage model (v1)
• Auto-routing engine
• Basic status tracking
Phase 2 — Visibility
Months 4–5
• SMS/push notifications
• Resident status portal
• Resident feedback on completion
• Duplicate detection
Phase 3 — Operations
Months 6–8
• Officer mobile app
• AI-prioritised queue
• Contractor digital app
• SLA breach alerts
Phase 4 — Intelligence
Months 9–10
• Analytics dashboard
• Predictive maintenance signals
• Contractor performance scoring
• Management reporting

## Slide 4
HOW TO USE THIS FILE
1
This PowerPoint is a sample Roadmap input file for CharterOS.
2
In CharterOS, navigate to the Product Roadmap section.
3
Click 'Upload Supporting Files' and upload this file.
4
The AI Roadmap Architect will read the epics and phases to generate a structured roadmap.
5
Edit Slide 2 (Epics) to reflect your team's actual priorities before uploading.
6
Edit Slide 3 (Phases) to adjust delivery sequencing as needed.