## Slide 1
Product Roadmap
Municipal Smart Sensor & IoT Network Platform
Estate Management Division
Sample Input File — For Upload into CharterOS

## Slide 2
PRODUCT EPICS
# | Epic Name | Duration | Priority | Owner | Key Outcome
1 | Sensor Infrastructure & Deployment | 4 months | HIGH | Tech Lead | 2 pilot estates fully wired with live data ingestion
2 | Real-Time Data Platform | 3 months | HIGH | Data Engineer | Live dashboard and estate digital twin
3 | AI Anomaly Detection Engine | 3 months | HIGH | Data Engineer | 92%+ precision, tiered alert system live
4 | Field Officer Mobile App | 2 months | MEDIUM | Tech Lead | Push alerts and GPS-tagged fault reporting
5 | Energy Optimisation Module | 2 months | LOW | Product Owner | 15% energy reduction in pilot estates

## Slide 3
DELIVERY PHASES
Phase 1 — Infrastructure
Months 1–4
• Sensor hardware selection
• Network topology design
• Pilot estate installation
• MQTT ingestion pipeline
Phase 2 — Platform
Months 5–7
• Time-series database
• Real-time dashboard
• Digital twin visualisation
• SNDGO data connector
Phase 3 — Intelligence
Months 8–10
• Anomaly detection model
• Tiered alert system
• False positive tuning
• Field officer mobile app
Phase 4 — Optimisation
Months 11–12
• Energy optimisation module
• Smart lighting controls
• BMS integration
• Estate expansion planning

## Slide 4
HOW TO USE THIS FILE
1
This PowerPoint is a sample Roadmap input file for CharterOS.
2
In CharterOS, navigate to the Product Roadmap section.
3
Click 'Upload Supporting Files' and upload this file.
4
The AI Roadmap Architect will read the epics and phases to generate a structured roadmap.
5
Edit Slide 2 (Epics) to reflect your team's actual priorities before uploading.
6
Edit Slide 3 (Phases) to adjust delivery sequencing as needed.