## Slide 1
Product Roadmap
Community Space Booking & Management System
Citizen Experience Group
Sample Input File — For Upload into CharterOS

## Slide 2
PRODUCT EPICS
# | Epic Name | Duration | Priority | Owner | Key Outcome
1 | Facility Discovery Portal | 2 months | HIGH | Product Manager | All facilities searchable with photos and real-time availability
2 | Online Booking & Payment Engine | 3 months | HIGH | Tech Lead | End-to-end booking with PayNow/card and auto deposit
3 | TC Admin Portal | 2 months | HIGH | Product Manager | TC staff fully manage facilities and bookings digitally
4 | Mobile App (iOS & Android) | 3 months | MEDIUM | Tech Lead | Native mobile experience with QR check-in
5 | Analytics & Optimisation | 2 months | LOW | Product Owner | Utilisation heatmaps and TC benchmarking

## Slide 3
DELIVERY PHASES
Phase 1 — Discovery
Months 1–2
• Facility data migration
• Search and browse UI
• Photo gallery
• Availability calendar
Phase 2 — Booking
Months 3–5
• Booking flow
• PayNow + card integration
• Deposit automation
• Booking confirmation emails
Phase 3 — Admin
Months 6–7
• TC admin portal
• Calendar blocking
• Revenue reporting
• Deposit refund management
Phase 4 — Mobile & Analytics
Months 8–10
• iOS/Android app
• QR code check-in
• Push notifications
• Utilisation analytics dashboard

## Slide 4
HOW TO USE THIS FILE
1
This PowerPoint is a sample Roadmap input file for CharterOS.
2
In CharterOS, navigate to the Product Roadmap section.
3
Click 'Upload Supporting Files' and upload this file.
4
The AI Roadmap Architect will read the epics and phases to generate a structured roadmap.
5
Edit Slide 2 (Epics) to reflect your team's actual priorities before uploading.
6
Edit Slide 3 (Phases) to adjust delivery sequencing as needed.