## Slide 1
Product Roadmap
Predictive Lift Maintenance Intelligence System
Building Infrastructure & Ops
Sample Input File — For Upload into CharterOS

## Slide 2
PRODUCT EPICS
# | Epic Name | Duration | Priority | Owner | Key Outcome
1 | Lift Telemetry Infrastructure | 4 months | HIGH | Tech Lead | Sensors live on 500 pilot lifts with real-time data stream
2 | Predictive ML Engine | 4 months | HIGH | Data Scientist | Daily health scores and failure predictions at 88%+ precision
3 | Maintenance Operations Dashboard | 2 months | HIGH | Product Manager | Live lift health map and predictive alert queue
4 | Contractor Mobile App | 2 months | MEDIUM | Tech Lead | Digital work orders and real-time SLA tracking
5 | Resident Communication Module | 1 month | MEDIUM | Product Manager | Proactive SMS with ETR during planned maintenance

## Slide 3
DELIVERY PHASES
Phase 1 — Telemetry
Months 1–4
• Sensor selection & procurement
• Pilot lift installation (500 lifts)
• Real-time data ingestion
• Sensor health monitoring
Phase 2 — Intelligence
Months 5–8
• ML model training
• Failure prediction scoring
• Daily health score generation
• Model explainability layer
Phase 3 — Operations
Months 9–10
• Operations dashboard
• Predictive alert queue
• Contractor dispatch system
• Contractor mobile app
Phase 4 — Scale & Comms
Months 11–12
• Scale to all 30,000 lifts
• Resident SMS notifications
• ETR communication engine
• Post-restoration feedback

## Slide 4
HOW TO USE THIS FILE
1
This PowerPoint is a sample Roadmap input file for CharterOS.
2
In CharterOS, navigate to the Product Roadmap section.
3
Click 'Upload Supporting Files' and upload this file.
4
The AI Roadmap Architect will read the epics and phases to generate a structured roadmap.
5
Edit Slide 2 (Epics) to reflect your team's actual priorities before uploading.
6
Edit Slide 3 (Phases) to adjust delivery sequencing as needed.