## One-Off Costs
One-Off Implementation Costs — Municipal Smart Sensor & IoT Network Platform
Upload in CharterOS → KPIs & Metrics → Cost Benefit Analysis → Cost Inputs tab
# | Cost Item | Category | Description | Amount (SGD) | Notes
1 | IoT Sensor Hardware (2 pilot estates) | Hardware | ~1,200 sensors incl. environmental, lighting, water pipe, lift sensors. Unit cost SGD 320 + SGD 80 installation. | 480000 | SGD 400 avg installed
2 | Network Infrastructure & Gateways | Infrastructure | 18 LoRaWAN gateways, edge nodes, network switches, structured cabling across Punggol and Sengkang. | 165000 | SGD ~9.2K per gateway installed
3 | Connectivity Setup & Year 1 Data Plans | Infrastructure | SIM provisioning, APN configuration, first-year 4G/5G data plans for all deployed sensors. | 28000 | One-time + Y1 data
4 | IoT Platform Development | Software | Data ingestion platform, MQTT broker, time-series DB, REST API, SNDGO data connector. 8-month build. | 420000 | Vendor + internal dev
5 | Real-Time Dashboard & Digital Twin | Software | Estate operations dashboard, alert management UI, estate digital twin visualisation. | 195000 | UX + frontend + backend
6 | AI Anomaly Detection Engine (v1) | Software / AI | Model development on 3 years historical data, anomaly classification, tiered alerts, explainability layer. | 185000 | Incl. data science + MLOps
7 | Field Officer Mobile App | Software | iOS & Android: push alerts, GPS fault reporting, work orders, inspection checklist. | 90000 | React Native cross-platform
8 | Energy Optimisation Module | Software | Smart lighting controls, BMS connector, energy analytics dashboard. | 75000 | Phase 4 delivery
9 | System Integration & UAT | Professional Services | End-to-end integration testing, UAT with estate managers, performance tuning, go-live support. | 125000 | 3-month engagement
10 | Change Management & Training | Professional Services | Estate manager training, field officer onboarding, contractor digital adoption workshops. | 55000 | 20 sessions
11 | Project Management (12 months) | Professional Services | Senior PM for full delivery lifecycle incl. vendor management and government reporting. | 150000 | SGD ~12.5K/month
12 | Cybersecurity & Compliance Review | Professional Services | IoT security assessment, SGTS compliance, penetration testing, data governance docs. | 68000 | Required for SNDGO
13 | Contingency (12%) | Contingency | Buffer for hardware delays, integration complexity, government approval cycles. | 253000 | 12% of items 1–12
TOTAL ONE-OFF INVESTMENT |  |  |  | 2289000

## Annual Recurring Costs
Annual Recurring Costs — Municipal Smart Sensor & IoT Network Platform
These costs apply from Year 1 onwards after go-live.
# | Cost Item | Category | Description | Amount (SGD) | Notes
1 | Sensor Maintenance & Replacement | Hardware | Annual vendor maintenance SLA + 5% replacement rate (60 units × SGD 400 avg). | 44000 | Vendor contract
2 | Cloud Infrastructure & Hosting | Infrastructure | AWS/Azure: IoT platform, time-series DB, dashboard, DR backup. | 48000 | ~SGD 4K/month
3 | Connectivity — Annual Data Plans | Infrastructure | 4G/5G SIM data plans for all deployed sensors. | 26000 | ~SGD 2.2K/month
4 | Platform Licences & Vendor Support | Software | Annual software licences, vendor support, security patches, platform updates. | 65000 | Annual agreement
5 | AI Model Retraining & Data Science | Software / AI | Quarterly retraining, false positive tuning, new anomaly patterns, MLOps. | 55000 | 0.55 FTE equiv.
6 | Managed Operations & NOC Support | Operations | 24/7 platform monitoring, incident response, field tech coordination. | 78000 | Outsourced NOC + ops
7 | Security & Compliance Maintenance | Operations | Annual audits, SGTS re-certification, vulnerability scanning. | 26000 | Annual cycle
8 | Estate Expansion (Years 2–3) | Hardware | Sensor hardware + installation for 3 additional estates/year (to hit 5-estate target). | 330000 | SGD 110K per estate
TOTAL ANNUAL RECURRING COST |  |  |  | 672000

## Cost Summary
Cost Summary — Municipal Smart Sensor & IoT Network Platform
ONE-OFF INVESTMENT
Total One-Off Cost | 2289000
ANNUAL RECURRING
Annual Recurring Cost | 672000
ANNUAL BENEFIT (pilot — 2 estates)
Total Annual Benefit | 1800000
PROJECTIONS
Year 1 Total Cost | 2961000
Year 2 Total Cost | 672000
Year 3 Total Cost | 672000
Net Year 1 | -1161000
Net Year 2 | 1128000
Net Year 3 | 1128000
3-Year Cumulative Net | 1095000
Estimated Payback Period | 24 months
3-Year ROI | 25%